## 📊 Overview
DataMind AI — Phase 1 Sprint Planner
Team Lead: Smita ¦ Phase 1: May 6 – June 10, 2026 ¦ 5 Sprints ¦ 78 Tasks
Sprint | Dates | Tasks | Points | Status | Completion %
Sprint 1 — Foundation | May 6–9 | 12 | 26 | Not Started | 0%
Sprint 2 — Ingestion + Domain | May 12–16 | 12 | 29 | Not Started | 0%
Sprint 3 — HITL #1 + Cleaning + LLM | May 19–23 | 14 | 38 | Not Started | 0%
Sprint 4 — HITL #2 + Storage + Dashboard | May 26–30 | 17 | 46 | Not Started | 0%
Sprint 5 — Admin UI + QA + Hardening | Jun 2–6 | 23 | 63 | Not Started | 0%
TOTAL | May 6 – Jun 10 | 78 | 202
Role Legend
BE — Backend Developer
FE — Frontend Developer
AI — AI / Agent Engineer
DO — DevOps / Infra
QA — QA Engineer
Status Legend
Not Started
In Progress
Done
Blocked

## Sprint1
Sprint 1 — Foundation
May 6–9, 2026 ¦ Goal: Repo live, auth working, infra provisioned, CI/CD green
Exit Criteria: User can sign up, log in, hit /health. CI/CD deploys to staging.
Task ID | Task Name | Role | Assignee | Priority | Points | Status | Start Date | Due Date | Depends On | Notes
S1-01 | Set up Git repo, branch strategy, PR template, CODEOWNERS | DO |  | P1 | 1 | Not Started |  |  | —
S1-02 | GitHub Actions CI/CD — lint, typecheck, unit tests, Docker build, staging deploy | DO |  | P1 | 3 | Not Started |  |  | S1-01
S1-03 | Provision AWS infra — S3 buckets (raw/curated/state/audit), RDS Postgres, Redis, IAM | DO |  | P1 | 3 | Not Started |  |  | —
S1-04 | Docker Compose for local dev — Postgres (pgvector) + Redis | DO |  | P1 | 2 | Not Started |  |  | —
S1-05 | FastAPI project structure — routers, middleware, dependencies, pyproject.toml | BE |  | P1 | 2 | Not Started |  |  | S1-04
S1-06 | DB schema + Alembic migrations — users, tenants, datasets, pipeline_runs, hitl_decisions, audit_events, jobs, llm_provider_config | BE |  | P1 | 3 | Not Started |  |  | S1-03,S1-04
S1-07 | JWT auth endpoints — /auth/signup, /auth/login, /auth/refresh, /auth/logout | BE |  | P1 | 3 | Not Started |  |  | S1-06
S1-08 | RBAC middleware — role claim enforcement on every FastAPI route | BE |  | P1 | 2 | Not Started |  |  | S1-07
S1-09 | GET /health — checks DB, Redis, S3 connectivity | BE |  | P1 | 1 | Not Started |  |  | S1-05,S1-03
S1-10 | Next.js 14 setup — TypeScript, Tailwind CSS, shadcn/ui, pnpm workspace | FE |  | P1 | 2 | Not Started |  |  | —
S1-11 | Sign up / Sign in screens (U1) — form validation, JWT storage, redirect logic | FE |  | P1 | 3 | Not Started |  |  | S1-07,S1-10
S1-12 | .env.example, local dev README, team onboarding docs | DO |  | P2 | 1 | Not Started |  |  | S1-04
Sprint Total: 12 tasks |  |  |  |  | 26

## Sprint2
Sprint 2 — Ingestion + Domain
May 12–16, 2026 ¦ Goal: Multi-file upload working. Domain persists. HITL #1 screen renders.
Exit Criteria: Domain persists to DB. Multi-file upload accepted. Schema preview visible.
Task ID | Task Name | Role | Assignee | Priority | Points | Status | Start Date | Due Date | Depends On | Notes
S2-01 | Domain selection screen (U2) — first-run modal, 6 options, free-text for Other | FE |  | P1 | 2 | Not Started |  |  | S1-11
S2-02 | PATCH /me/domain — update active domain on user profile | BE |  | P1 | 1 | Not Started |  |  | S1-08
S2-03 | File upload screen (U3) — drag-and-drop, multi-file, format validation, progress bar | FE |  | P1 | 3 | Not Started |  |  | S1-11
S2-04 | POST /datasets/upload-url — generate presigned S3 URLs for direct browser upload | BE |  | P1 | 2 | Not Started |  |  | S1-08
S2-05 | POST /datasets/{id}/ingest — enqueue Celery ingestion job, return job_id | BE |  | P1 | 2 | Not Started |  |  | S2-04
S2-06 | Ingestion Agent — format detection (mime + content sniff) CSV/XLSX/JSON/Parquet | AI |  | P1 | 3 | Not Started |  |  | S1-05
S2-07 | Ingestion Agent — parsing + column profiling (dtype, null count, distinct, avg length) | AI |  | P1 | 3 | Not Started |  |  | S2-06
S2-08 | Ingestion Agent — multi-file merge plan (UNION vs JOIN, merge key, confidence) | AI |  | P1 | 3 | Not Started |  |  | S2-07
S2-09 | Column type classification — numeric / textual / ambiguous routing rules | AI |  | P1 | 2 | Not Started |  |  | S2-07
S2-10 | Domain Agent — prompt pack loader, Postgres lookup per domain | AI |  | P1 | 2 | Not Started |  |  | S1-06
S2-11 | Domain prompt packs — Finance, Healthcare, Retail, Marketing, Other (YAML, versioned) | AI |  | P1 | 4 | Not Started |  |  | S2-10
S2-12 | GET /jobs/{id} — poll job status, progress %, current step | BE |  | P1 | 2 | Not Started |  |  | S2-05
Sprint Total: 12 tasks |  |  |  |  | 29

## Sprint3
Sprint 3 — HITL #1 + Cleaning Plan + LLM Abstraction
May 19–23, 2026 ¦ Goal: Cleaning plan generated. HITL #1 screen done. LLM abstraction live.
Exit Criteria: Cleaning plan generated and displayed. ≥ 60% acceptance on golden datasets 1–5.
Task ID | Task Name | Role | Assignee | Priority | Points | Status | Start Date | Due Date | Depends On | Notes
S3-01 | Schema & merge validation screen (HITL #1, U4) — schema table, type-routing badges, merge plan | FE |  | P1 | 4 | Not Started |  |  | S2-03,S2-12
S3-02 | HITL #1 interactions — type-routing override, merge key change, exclude column/file | FE |  | P1 | 3 | Not Started |  |  | S3-01
S3-03 | GET /datasets/{id}/merge-plan — return ingestion profile with schema + merge proposal | BE |  | P1 | 2 | Not Started |  |  | S2-05
S3-04 | POST /datasets/{id}/merge-plan/decision — record decision in hitl_decisions, enqueue next | BE |  | P1 | 2 | Not Started |  |  | S3-03
S3-05 | LangGraph Supervisor — state machine, step routing, HITL pause/resume, retry on failure | AI |  | P1 | 4 | Not Started |  |  | S1-05
S3-06 | HITL Gate Manager — pause_pipeline_for_decision(), resume_pipeline_with_decision() | AI |  | P1 | 3 | Not Started |  |  | S3-05
S3-07 | Pipeline state persistence — serialise state to S3 + Postgres after every agent step | BE |  | P1 | 3 | Not Started |  |  | S3-05,S1-03
S3-08 | LLM Provider Abstraction — LiteLLM-compatible, structured_completion(), Pydantic validation, retry (3×) | AI |  | P1 | 4 | Not Started |  |  | S1-05
S3-09 | Anthropic Claude provider — Secrets Manager key, structured JSON, token/cost/latency logging | AI |  | P1 | 2 | Not Started |  |  | S3-08
S3-10 | OpenAI provider — Secrets Manager key, structured JSON, token/cost/latency logging | AI |  | P1 | 2 | Not Started |  |  | S3-08
S3-11 | Cleaning Plan Agent — exact dedup + imputation strategy (median/mean/mode/drop/leave) | AI |  | P1 | 3 | Not Started |  |  | S3-05,S3-08
S3-12 | Cleaning Plan Agent — type coercion proposals + basic outlier flagging (no auto-fix) | AI |  | P1 | 3 | Not Started |  |  | S3-11
S3-13 | Confidence scoring — 0.0–1.0 per step, colour thresholds (red/orange/yellow) | AI |  | P1 | 2 | Not Started |  |  | S3-11
S3-14 | GET /datasets/{id}/cleaning-plan — return numbered steps with rationale + confidence | BE |  | P1 | 1 | Not Started |  |  | S3-11
Sprint Total: 14 tasks |  |  |  |  | 38

## Sprint4
Sprint 4 — HITL #2 + Storage + Analysis + Dashboard
May 26–30, 2026 ¦ Goal: Full end-to-end pipeline working. Dashboard renders within 90s.
Exit Criteria: E2E happy path works for CSV and Parquet merge. Dashboard renders within 90s.
Task ID | Task Name | Role | Assignee | Priority | Points | Status | Start Date | Due Date | Depends On | Notes
S4-01 | Cleaning plan review screen (HITL #2, U5) — numbered steps, confidence badges, per-step controls | FE |  | P1 | 4 | Not Started |  |  | S3-01,S3-14
S4-02 | Modify step UI — imputation strategy picker, column exclusion, custom value input | FE |  | P1 | 3 | Not Started |  |  | S4-01
S4-03 | POST /datasets/{id}/cleaning-plan/decision — record approved/modified/rejected steps | BE |  | P1 | 2 | Not Started |  |  | S3-04
S4-04 | Cleaning Executor Agent — run only approved steps, write audit event per step | AI |  | P1 | 3 | Not Started |  |  | S3-11,S4-03
S4-05 | Write cleaned data to curated S3 Parquet (Layer 2) — versioned per cleaning run | BE |  | P1 | 2 | Not Started |  |  | S4-04
S4-06 | Load numeric columns into Postgres table (Layer 3) — one typed table per dataset_id | BE |  | P1 | 3 | Not Started |  |  | S4-05
S4-07 | Embed textual columns + load into pgvector (Layer 4) — HNSW index, per-tenant namespace | AI |  | P1 | 3 | Not Started |  |  | S4-05
S4-08 | Intent capture screen (U6) — free-text input, domain suggestion chips, HITL #3 confirmation | FE |  | P1 | 3 | Not Started |  |  | S4-01
S4-09 | POST /datasets/{id}/intent — submit intent, return restated interpretation for HITL #3 | BE |  | P1 | 1 | Not Started |  |  | S4-05
S4-10 | Intent Agent — free-text → structured AnalysisSpec, biased by domain pack + schema | AI |  | P1 | 3 | Not Started |  |  | S3-08,S3-05
S4-11 | Analysis Agent — SQL builder (sqlglot) + DuckDB runner for numeric (Layer 3) | AI |  | P1 | 3 | Not Started |  |  | S4-06,S4-10
S4-12 | Analysis Agent — pgvector semantic search for textual questions (Layer 4) | AI |  | P1 | 3 | Not Started |  |  | S4-07,S4-10
S4-13 | SQL safety validation — sqlglot parse, block all non-SELECT statements | BE |  | P1 | 2 | Not Started |  |  | S4-11
S4-14 | POST /dashboards/generate — enqueue dashboard job, return job_id | BE |  | P1 | 1 | Not Started |  |  | S4-11
S4-15 | Dashboard Agent — Vega-Lite spec (2–3 KPI cards + 2 charts: bar/line/table) | AI |  | P1 | 4 | Not Started |  |  | S4-11,S4-12
S4-16 | Insights Agent — domain-flavoured narrative + recommended action, factual consistency check | AI |  | P1 | 3 | Not Started |  |  | S4-15
S4-17 | Dashboard screen (U7) — render KPI cards + Vega-Lite charts + narrative, poll until ready | FE |  | P1 | 4 | Not Started |  |  | S4-15
Sprint Total: 17 tasks |  |  |  |  | 47

## Sprint5
Sprint 5 — Admin UI + QA + Hardening
Jun 2–6, 2026 ¦ Goal: Internal beta ready. All Phase 1 acceptance criteria met.
Exit Criteria: Internal beta with 5 users for 1 week. All NFR targets verified.
Task ID | Task Name | Role | Assignee | Priority | Points | Status | Start Date | Due Date | Depends On | Notes
S5-01 | Admin UI — System Health (A1): pipeline status, queue depth, error rates | FE |  | P1 | 2 | Not Started |  |  | S1-11
S5-02 | Admin UI — User & Role Management (A2): list, invite, suspend, change role | FE |  | P1 | 3 | Not Started |  |  | S5-01
S5-03 | Admin UI — LLM Provider Config (A3): provider, model, per-agent routing | FE |  | P1 | 3 | Not Started |  |  | S5-01
S5-04 | Admin UI — Domain Pack Viewer (A4): read-only pack viewer | FE |  | P2 | 2 | Not Started |  |  | S5-01
S5-05 | Admin UI — Audit Log Viewer (A5): search HITL decisions + cleaning actions | FE |  | P1 | 2 | Not Started |  |  | S5-01
S5-06 | History / Audit screen for users (U8): past runs, downloadable audit log (JSON/CSV) | FE |  | P2 | 2 | Not Started |  |  | S4-17
S5-07 | All admin API endpoints — /admin/users, /admin/llm-providers, /admin/domain-packs, /admin/health, /admin/audit | BE |  | P1 | 4 | Not Started |  |  | S1-08
S5-08 | GET /jobs/{id}/audit — return full audit log for a pipeline run | BE |  | P1 | 1 | Not Started |  |  | S4-04
S5-09 | AWS Secrets Manager integration — retrieve LLM API keys per tenant at runtime | DO |  | P1 | 2 | Not Started |  |  | S3-09,S3-10
S5-10 | CloudWatch structured logging — JSON logs per request + per agent step | DO |  | P1 | 2 | Not Started |  |  | S1-02
S5-11 | CloudWatch alerting — all 7 alert conditions (failure rate, latency, S3, LLM error, HITL queue, spend, confidence) | DO |  | P1 | 3 | Not Started |  |  | S5-10
S5-12 | Staging deployment — ECS task definition, ECR image, RDS migration on deploy | DO |  | P1 | 3 | Not Started |  |  | S1-02,S1-03
S5-13 | Unit tests — agent functions, transform logic, API handlers (≥ 70% coverage) | QA |  | P1 | 3 | Not Started |  |  | S4-16
S5-14 | Integration tests — agent-to-agent, S3, DuckDB, pgvector (happy paths + key errors) | QA |  | P1 | 3 | Not Started |  |  | S4-16
S5-15 | E2E tests — single-file pipeline for all 4 formats (CSV, XLSX, JSON, Parquet) | QA |  | P1 | 4 | Not Started |  |  | S4-17
S5-16 | E2E tests — multi-file (2-file + 5-file, union + join paths) | QA |  | P1 | 3 | Not Started |  |  | S4-17
S5-17 | HITL flow tests — all decision branches per gate (#1, #2, #3) | QA |  | P1 | 3 | Not Started |  |  | S4-17
S5-18 | RBAC enforcement tests — 403 for all admin routes with non-admin token | QA |  | P1 | 2 | Not Started |  |  | S5-07
S5-19 | LLM portability tests — full pipeline on Claude + OpenAI, no quality regression | QA |  | P1 | 3 | Not Started |  |  | S5-14
S5-20 | Performance tests — 50MB file, p95 dashboard latency < 90s, HITL cycle < 90s median | QA |  | P1 | 2 | Not Started |  |  | S5-15
S5-21 | Golden dataset validation — 10 datasets, ≥ 70% cleaning acceptance | QA |  | P1 | 4 | Not Started |  |  | S5-15
S5-22 | Bug fixes + polish from QA findings | ALL |  | P1 | 4 | Not Started |  |  | S5-21
S5-23 | Internal beta setup — 5 users onboarded, staging access, feedback collection | DO |  | P1 | 2 | Not Started |  |  | S5-12
Sprint Total: 23 tasks |  |  |  |  | 62

## 🗂 Master Tracker
DataMind AI — Phase 1 Master Task Tracker
Task ID | Task Name | Role | Assignee | Priority | Points | Status | Start Date | Due Date | Depends On | Notes
Sprint 1 — Foundation ¦ May 6–9, 2026
S1-01 | Set up Git repo, branch strategy, PR template, CODEOWNERS | DO |  | P1 | 1 | Not Started |  |  | —
S1-02 | GitHub Actions CI/CD — lint, typecheck, unit tests, Docker build, staging deploy | DO |  | P1 | 3 | Not Started |  |  | S1-01
S1-03 | Provision AWS infra — S3 buckets (raw/curated/state/audit), RDS Postgres, Redis, IAM | DO |  | P1 | 3 | Not Started |  |  | —
S1-04 | Docker Compose for local dev — Postgres (pgvector) + Redis | DO |  | P1 | 2 | Not Started |  |  | —
S1-05 | FastAPI project structure — routers, middleware, dependencies, pyproject.toml | BE |  | P1 | 2 | Not Started |  |  | S1-04
S1-06 | DB schema + Alembic migrations — users, tenants, datasets, pipeline_runs, hitl_decisions, audit_events, jobs, llm_provider_config | BE |  | P1 | 3 | Not Started |  |  | S1-03,S1-04
S1-07 | JWT auth endpoints — /auth/signup, /auth/login, /auth/refresh, /auth/logout | BE |  | P1 | 3 | Not Started |  |  | S1-06
S1-08 | RBAC middleware — role claim enforcement on every FastAPI route | BE |  | P1 | 2 | Not Started |  |  | S1-07
S1-09 | GET /health — checks DB, Redis, S3 connectivity | BE |  | P1 | 1 | Not Started |  |  | S1-05,S1-03
S1-10 | Next.js 14 setup — TypeScript, Tailwind CSS, shadcn/ui, pnpm workspace | FE |  | P1 | 2 | Not Started |  |  | —
S1-11 | Sign up / Sign in screens (U1) — form validation, JWT storage, redirect logic | FE |  | P1 | 3 | Not Started |  |  | S1-07,S1-10
S1-12 | .env.example, local dev README, team onboarding docs | DO |  | P2 | 1 | Not Started |  |  | S1-04
Sprint 2 — Ingestion + Domain ¦ May 12–16, 2026
S2-01 | Domain selection screen (U2) — first-run modal, 6 options, free-text for Other | FE |  | P1 | 2 | Not Started |  |  | S1-11
S2-02 | PATCH /me/domain — update active domain on user profile | BE |  | P1 | 1 | Not Started |  |  | S1-08
S2-03 | File upload screen (U3) — drag-and-drop, multi-file, format validation, progress bar | FE |  | P1 | 3 | Not Started |  |  | S1-11
S2-04 | POST /datasets/upload-url — generate presigned S3 URLs for direct browser upload | BE |  | P1 | 2 | Not Started |  |  | S1-08
S2-05 | POST /datasets/{id}/ingest — enqueue Celery ingestion job, return job_id | BE |  | P1 | 2 | Not Started |  |  | S2-04
S2-06 | Ingestion Agent — format detection (mime + content sniff) CSV/XLSX/JSON/Parquet | AI |  | P1 | 3 | Not Started |  |  | S1-05
S2-07 | Ingestion Agent — parsing + column profiling (dtype, null count, distinct, avg length) | AI |  | P1 | 3 | Not Started |  |  | S2-06
S2-08 | Ingestion Agent — multi-file merge plan (UNION vs JOIN, merge key, confidence) | AI |  | P1 | 3 | Not Started |  |  | S2-07
S2-09 | Column type classification — numeric / textual / ambiguous routing rules | AI |  | P1 | 2 | Not Started |  |  | S2-07
S2-10 | Domain Agent — prompt pack loader, Postgres lookup per domain | AI |  | P1 | 2 | Not Started |  |  | S1-06
S2-11 | Domain prompt packs — Finance, Healthcare, Retail, Marketing, Other (YAML, versioned) | AI |  | P1 | 4 | Not Started |  |  | S2-10
S2-12 | GET /jobs/{id} — poll job status, progress %, current step | BE |  | P1 | 2 | Not Started |  |  | S2-05
Sprint 3 — HITL #1 + Cleaning Plan + LLM Abstraction ¦ May 19–23, 2026
S3-01 | Schema & merge validation screen (HITL #1, U4) — schema table, type-routing badges, merge plan | FE |  | P1 | 4 | Not Started |  |  | S2-03,S2-12
S3-02 | HITL #1 interactions — type-routing override, merge key change, exclude column/file | FE |  | P1 | 3 | Not Started |  |  | S3-01
S3-03 | GET /datasets/{id}/merge-plan — return ingestion profile with schema + merge proposal | BE |  | P1 | 2 | Not Started |  |  | S2-05
S3-04 | POST /datasets/{id}/merge-plan/decision — record decision in hitl_decisions, enqueue next | BE |  | P1 | 2 | Not Started |  |  | S3-03
S3-05 | LangGraph Supervisor — state machine, step routing, HITL pause/resume, retry on failure | AI |  | P1 | 4 | Not Started |  |  | S1-05
S3-06 | HITL Gate Manager — pause_pipeline_for_decision(), resume_pipeline_with_decision() | AI |  | P1 | 3 | Not Started |  |  | S3-05
S3-07 | Pipeline state persistence — serialise state to S3 + Postgres after every agent step | BE |  | P1 | 3 | Not Started |  |  | S3-05,S1-03
S3-08 | LLM Provider Abstraction — LiteLLM-compatible, structured_completion(), Pydantic validation, retry (3×) | AI |  | P1 | 4 | Not Started |  |  | S1-05
S3-09 | Anthropic Claude provider — Secrets Manager key, structured JSON, token/cost/latency logging | AI |  | P1 | 2 | Not Started |  |  | S3-08
S3-10 | OpenAI provider — Secrets Manager key, structured JSON, token/cost/latency logging | AI |  | P1 | 2 | Not Started |  |  | S3-08
S3-11 | Cleaning Plan Agent — exact dedup + imputation strategy (median/mean/mode/drop/leave) | AI |  | P1 | 3 | Not Started |  |  | S3-05,S3-08
S3-12 | Cleaning Plan Agent — type coercion proposals + basic outlier flagging (no auto-fix) | AI |  | P1 | 3 | Not Started |  |  | S3-11
S3-13 | Confidence scoring — 0.0–1.0 per step, colour thresholds (red/orange/yellow) | AI |  | P1 | 2 | Not Started |  |  | S3-11
S3-14 | GET /datasets/{id}/cleaning-plan — return numbered steps with rationale + confidence | BE |  | P1 | 1 | Not Started |  |  | S3-11
Sprint 4 — HITL #2 + Storage + Analysis + Dashboard ¦ May 26–30, 2026
S4-01 | Cleaning plan review screen (HITL #2, U5) — numbered steps, confidence badges, per-step controls | FE |  | P1 | 4 | Not Started |  |  | S3-01,S3-14
S4-02 | Modify step UI — imputation strategy picker, column exclusion, custom value input | FE |  | P1 | 3 | Not Started |  |  | S4-01
S4-03 | POST /datasets/{id}/cleaning-plan/decision — record approved/modified/rejected steps | BE |  | P1 | 2 | Not Started |  |  | S3-04
S4-04 | Cleaning Executor Agent — run only approved steps, write audit event per step | AI |  | P1 | 3 | Not Started |  |  | S3-11,S4-03
S4-05 | Write cleaned data to curated S3 Parquet (Layer 2) — versioned per cleaning run | BE |  | P1 | 2 | Not Started |  |  | S4-04
S4-06 | Load numeric columns into Postgres table (Layer 3) — one typed table per dataset_id | BE |  | P1 | 3 | Not Started |  |  | S4-05
S4-07 | Embed textual columns + load into pgvector (Layer 4) — HNSW index, per-tenant namespace | AI |  | P1 | 3 | Not Started |  |  | S4-05
S4-08 | Intent capture screen (U6) — free-text input, domain suggestion chips, HITL #3 confirmation | FE |  | P1 | 3 | Not Started |  |  | S4-01
S4-09 | POST /datasets/{id}/intent — submit intent, return restated interpretation for HITL #3 | BE |  | P1 | 1 | Not Started |  |  | S4-05
S4-10 | Intent Agent — free-text → structured AnalysisSpec, biased by domain pack + schema | AI |  | P1 | 3 | Not Started |  |  | S3-08,S3-05
S4-11 | Analysis Agent — SQL builder (sqlglot) + DuckDB runner for numeric (Layer 3) | AI |  | P1 | 3 | Not Started |  |  | S4-06,S4-10
S4-12 | Analysis Agent — pgvector semantic search for textual questions (Layer 4) | AI |  | P1 | 3 | Not Started |  |  | S4-07,S4-10
S4-13 | SQL safety validation — sqlglot parse, block all non-SELECT statements | BE |  | P1 | 2 | Not Started |  |  | S4-11
S4-14 | POST /dashboards/generate — enqueue dashboard job, return job_id | BE |  | P1 | 1 | Not Started |  |  | S4-11
S4-15 | Dashboard Agent — Vega-Lite spec (2–3 KPI cards + 2 charts: bar/line/table) | AI |  | P1 | 4 | Not Started |  |  | S4-11,S4-12
S4-16 | Insights Agent — domain-flavoured narrative + recommended action, factual consistency check | AI |  | P1 | 3 | Not Started |  |  | S4-15
S4-17 | Dashboard screen (U7) — render KPI cards + Vega-Lite charts + narrative, poll until ready | FE |  | P1 | 4 | Not Started |  |  | S4-15
Sprint 5 — Admin UI + QA + Hardening ¦ Jun 2–6, 2026
S5-01 | Admin UI — System Health (A1): pipeline status, queue depth, error rates | FE |  | P1 | 2 | Not Started |  |  | S1-11
S5-02 | Admin UI — User & Role Management (A2): list, invite, suspend, change role | FE |  | P1 | 3 | Not Started |  |  | S5-01
S5-03 | Admin UI — LLM Provider Config (A3): provider, model, per-agent routing | FE |  | P1 | 3 | Not Started |  |  | S5-01
S5-04 | Admin UI — Domain Pack Viewer (A4): read-only pack viewer | FE |  | P2 | 2 | Not Started |  |  | S5-01
S5-05 | Admin UI — Audit Log Viewer (A5): search HITL decisions + cleaning actions | FE |  | P1 | 2 | Not Started |  |  | S5-01
S5-06 | History / Audit screen for users (U8): past runs, downloadable audit log (JSON/CSV) | FE |  | P2 | 2 | Not Started |  |  | S4-17
S5-07 | All admin API endpoints — /admin/users, /admin/llm-providers, /admin/domain-packs, /admin/health, /admin/audit | BE |  | P1 | 4 | Not Started |  |  | S1-08
S5-08 | GET /jobs/{id}/audit — return full audit log for a pipeline run | BE |  | P1 | 1 | Not Started |  |  | S4-04
S5-09 | AWS Secrets Manager integration — retrieve LLM API keys per tenant at runtime | DO |  | P1 | 2 | Not Started |  |  | S3-09,S3-10
S5-10 | CloudWatch structured logging — JSON logs per request + per agent step | DO |  | P1 | 2 | Not Started |  |  | S1-02
S5-11 | CloudWatch alerting — all 7 alert conditions (failure rate, latency, S3, LLM error, HITL queue, spend, confidence) | DO |  | P1 | 3 | Not Started |  |  | S5-10
S5-12 | Staging deployment — ECS task definition, ECR image, RDS migration on deploy | DO |  | P1 | 3 | Not Started |  |  | S1-02,S1-03
S5-13 | Unit tests — agent functions, transform logic, API handlers (≥ 70% coverage) | QA |  | P1 | 3 | Not Started |  |  | S4-16
S5-14 | Integration tests — agent-to-agent, S3, DuckDB, pgvector (happy paths + key errors) | QA |  | P1 | 3 | Not Started |  |  | S4-16
S5-15 | E2E tests — single-file pipeline for all 4 formats (CSV, XLSX, JSON, Parquet) | QA |  | P1 | 4 | Not Started |  |  | S4-17
S5-16 | E2E tests — multi-file (2-file + 5-file, union + join paths) | QA |  | P1 | 3 | Not Started |  |  | S4-17
S5-17 | HITL flow tests — all decision branches per gate (#1, #2, #3) | QA |  | P1 | 3 | Not Started |  |  | S4-17
S5-18 | RBAC enforcement tests — 403 for all admin routes with non-admin token | QA |  | P1 | 2 | Not Started |  |  | S5-07
S5-19 | LLM portability tests — full pipeline on Claude + OpenAI, no quality regression | QA |  | P1 | 3 | Not Started |  |  | S5-14
S5-20 | Performance tests — 50MB file, p95 dashboard latency < 90s, HITL cycle < 90s median | QA |  | P1 | 2 | Not Started |  |  | S5-15
S5-21 | Golden dataset validation — 10 datasets, ≥ 70% cleaning acceptance | QA |  | P1 | 4 | Not Started |  |  | S5-15
S5-22 | Bug fixes + polish from QA findings | ALL |  | P1 | 4 | Not Started |  |  | S5-21
S5-23 | Internal beta setup — 5 users onboarded, staging access, feedback collection | DO |  | P1 | 2 | Not Started |  |  | S5-12